## Slide 1
Modern Software Development Practices
Project Management Module
SESSION 3

## Slide 2: Agenda
Context setting
Quality Management
Risk Management
Project Monitoring and Control

## Slide 3: Recap of Previous Session

## Slide 4: Project Management Phases
Initiation
Closing
Planning
Executing
Monitoring & Control
Define a new project or new phase, identify stakeholders, and obtain authorization “Authorize the Work” | Develop an integrated project management plan to attain project objectives “Plan the Work” | Complete the work and satisfy project Objectives “Work the Plan | Track and review project progress and performance; manage variance and change “Control the Plan | Finalize all activities and formally close the project or phase “End the Work”
• Project Charter • Stakeholder Register | •Project Mgt. Plans & Related Documents - Scope - Requirements Schedule Cost Quality Human Resources Communication Risk Procurement Change Stakeholders | • Project Deliverables • Work Performance Data • Team Performance Assessments • Project Communications (e.g. status reports) • Selected Suppliers & Agreements • Change Requests • Issue Log | • Change Logs • Approved Change Requests • Work Performance Information • Schedule Forecasts • Cost Forecasts • Updates to Project Plan • Quality Control Measurements • Verified Deliverable • Accepted Deliverable | • Final Product, Service, or Result (i.e. purpose of project) • Closed Procurement (e.g. formal signature of acceptance)
Process Groups
Activities
Key Outputs

## Slide 5: Quality Management
Quality Management is the process to ensure that the project will satisfy the needs of the beneficiaries. Quality is defined as a commitment to deliver the project outputs and meet the expectations of the beneficiaries which means that quality is ultimately defined by the beneficiary.

## Slide 6: Quality Management
Project Quality Management ensures the project will satisfy NEEDS for which it was undertaken.
Plan Quality
Perform Quality Assurance
Perform Quality control
What is Quality ?
Conformance to specifications
Fitness for use.

## Slide 7: Quality Management
There are four steps in Quality management:
Quality Definition
Quality Assurance
Quality Control
Quality improvements

## Slide 8: Quality Management
The most popular tool used to determine quality assurance is the Shewhart Cycle.
This cycle for quality assurance consists of four steps: Plan, Do, Check and Act. These steps are commonly abbreviated as PDCA.

## Slide 9: Project monitoring
Regular reviews of progress against schedule using WBS as basis (Plan against Baseline)
Regular review of actual costs
Regular review of resource loading
Regular progress meetings with project team
Regular meetings with contractors
Production of periodic progress reports
Risk reviews
Inspections/ audits

## Slide 10: Project monitoring and control
Monitoring – collecting, recording and reporting information concerning project performance that project manager and others wish to know.
Controlling – uses data from monitor activity to bring actual performance to planned performance

## Slide 11: Project monitoring and control
Why do we monitor?
What do we monitor?
When do we monitor?
How do we monitor?

## Slide 12: Why do we monitor?
Simply because we know that things don’t always go according to plan (no matter how much we prepare)
To detect and react appropriately to deviations and changes to plan.

## Slide 13: What do we Monitor?
Human Resources
Space
Machines
Materials
Money
Time
Tasks
Quality

## Slide 14: What do we Monitor?
Inputs
Time
Money
Resources
Tasks
Quality
Outputs
Progress
Cost
Job Start
Design changes
Variation

## Slide 15: When do we Monitor?
End of Project
Continuously
Regularly
Logically
While there is still time to react
As soon as possible
At task completion
At pre-planned decision points (Milestones)

## Slide 16: How do we Monitor?
Through meetings with client, parties involved in project
For schedule – Update PERT charts, Gantt charts
Milestones
Reports
Test and inspections
Delivery or staggered delivery

## Slide 17: Meetings – Some monitoring issues
What problems do you have and what is being done to correct them?
What problems do you anticipate in future?
Do you need any resources you do not yet have?
Do you need information you do not have yet?
Do you know anything that will give you schedule difficulties?
Any possibilities your task will finish early/late?
Will your task be completed under/over/on budget.

## Slide 18: Project Control Cycle

## Slide 19: Project Control
Control – process and activities needed to correct deviations from plan
Control the triple constraints
  Time (schedule)
  Cost (budget, expenses etc)
  Performance (specifications, testing, results, etc)

## Slide 20: Project closure
Acceptance of deliverables
Lessons learnt
Release of resources

## Slide 21: Project management methodology - Agile
Waterfall employs a sequential, top-down approach to project management, where project managers reduce risk and uncertainty by outlining all the steps in a project and defining its scope, budget, and schedule upfront. In Waterfall, one phase of a project must be 100% successfully completed before moving onto the next phase.
The driving idea here is that you can save time and money by making sure everything is well-planned and all requirements are gathered at the outset of a project.

## Slide 22: Project management methodology - Agile
Agile lends itself to faster turnaround and the ability to quickly adapt to needed changes or course corrections, based in ongoing feedback. It takes a more people-centric perspective, implementing short, iterative phases called ‘sprints
After its success in the software development realm, Agile has seen a rapid rise among marketing groups. Marketing and creative teams say Agile frees them from the endless development cycles that often occur with more traditional task management methodologies, while giving their creativity a major boost.

## Slide 23: Project estimation
Estimation is the process of finding an estimate, or approximation, which is a value that can be used for some purpose even if input data may be incomplete, uncertain, or unstable.
Estimation determines how much money, effort, resources, and time it will take to build a specific system or product. Estimation is based on −
  Past Data/Past Experience
  Available Documents/Knowledge
  Assumptions
  Identified Risks

## Slide 24: Project estimation
Estimation need not be a one-time task in a project. It can take place during −
  Acquiring a Project.
  Planning the Project.
  Execution of the Project as the need arises.
The four basic steps in Software Project Estimation are
  Estimate the size of the development product.
  Estimate the effort in person-months or person-hours.
  Estimate the schedule in calendar months.
  Estimate the project cost in agreed currency.

## Slide 25: Project estimation - Accuracy
Accuracy is an indication of how close something is to reality. Whenever you generate an estimate, everyone wants to know how close the numbers are to reality. You will want every estimate to be as accurate as possible, given the data you have at the time you generate it. And of course you don’t want to present an estimate in a way that inspires a false sense of confidence in the numbers.
Important factors that affect the accuracy of estimates are
  The accuracy of all the estimate’s input data.
  The accuracy of any estimate calculation.
  How closely the historical data or industry data used to calibrate the model matches the project you are estimating.
  The predictability of your organization’s software development process

## Slide 26: Websites to look at as Project Management
https://www.pmi.org – Project Management
https://www.cebglobal.com/ -(PMO Leadership Council)
https://www.projectmanagement.com/- Webnairs
https://www.capterra.com/project-management-software/– Project Management Tools
https://www.slideshare.net/ostephens/project-management-tools-2014562- Project Management Tools
https://www.pmbypm.com/difference-project-program-and-portfolio/
https://www.youtube.com/watch?v=9LSnINglkQA
https://www.youtube.com/watch?v=6Or_9IRQHi4

## Slide 27
Thank You